## Project schedule
| ADAS Scheduling | 2024-10-22 |  |  |  |  | Project start: | [7 empty] | 2024-11-17
[7 empty] | Display week: | [7 empty] | 1
[7 empty] | 2024-11-18 | [6 empty] | 2024-11-25 | [6 empty] | 2024-12-02 | [6 empty] | 2024-12-09 | [6 empty] | 2024-12-16 | [6 empty] | 2024-12-23 | [6 empty] | 2024-12-30 | [6 empty] | 2025-01-06 | [6 empty] | 2025-01-13 | [6 empty] | 2025-01-20
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2024-11-18 to 2025-01-26
 | time axis 2024-11-18 to 2025-01-26
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
| Car Prototype Design (2 weeks) |  |  | 2024-10-23 | 2024-11-06 | 15
| Design the basic car chassis, including steering mechanism and body | Omar & Essam | 20% | 2024-10-23 | 2024-11-06 | 15
| Integrate the Ackerman steering design . | Magdy & Abanob | 0% | 2024-10-23 | 2024-11-06 | 15
| Create CAD models and prepare the car for simulation. | Omar & Essam & abanob | 0% | 2024-10-23 | 2024-11-06 | 15
| Revise, Report Writing and gantt Chart Update | Kareem & Omar & Magdy | 0% | 2024-10-23 | 2024-11-06 | 15
Ackerman Chassis Simulation (1 week)
| Run basic steering simulations for the Ackerman chassis. |  | 0% | 2024-11-06 | 2024-11-13 | 8
| Analyze the results and fine-tune the steering geometry for smooth turning. |  | 0% | 2024-11-06 | 2024-11-13 | 8
| Finalize the Ackerman steering system for integration with other ADAS features. |  | 0% | 2024-11-06 | 2024-11-13 | 8
| Testing and validation |  | 0% | 2024-11-06 | 2024-11-13 | 8
| Revise, Report Writing and gantt Chart Update |  | 0% | 2024-11-06 | 2024-11-13 | 8
Blind Spot Detection – Algorithm Development (2 weeks)
| Develop the blind spot detection algorithm using LiDAR or ultrasonic sensor data. |  | 0% | 2024-11-02 | 2024-11-13 | 12
| Simulate the algorithm for detecting obstacles in the car’s blind spots. |  | 0% | 2024-11-02 | 2024-11-13 | 12
| Optimize detection accuracy and performance. |  | 0% | 2024-11-02 | 2024-11-13 | 12
| Testing and validation |  | 0% | 2024-11-02 | 2024-11-13 | 12
| Revise, Report Writing and gantt Chart Update |  | 0% | 2024-11-02 | 2024-11-13 | 12
Lane Keeping Assist – Algorithm Development (2 weeks)
| Develop lane detection algorithms using camera data and image processing (OpenCV or machine learning). |  | 0% | 2024-11-06 | 2024-11-20 | 15
| Test and simulate the lane-keeping logic (e.g., PID control). |  | 0% | 2024-11-06 | 2024-11-20 | 15
| Optimize lane detection and steering adjustments for lane-keeping accuracy. |  | 0% | 2024-11-06 | 2024-11-20 | 15
| Testing and validation |  | 0% | 2024-11-06 | 2024-11-20 | 15
| Revise and Report Writing gantt Chart Update |  | 0% | 2024-11-06 | 2024-11-20 | 15
Adaptive Cruise Control – Algorithm Development (3 weeks)
| Develop the adaptive cruise control logic (speed regulation based on proximity to other vehicles). |  | 0% | 2024-11-13 | 2024-11-27 | 15
| Simulate speed and distance control with sensor data. |  | 0% | 2024-11-13 | 2024-11-27
| Test and fine-tune the adaptive cruise control for smooth vehicle operation. |  | 0% | 2024-11-13 | 2024-11-27
| Revise, Report Writing and gantt Chart Update |  | 0% | 2024-11-13 | 2024-11-27
Full System Integration and Simulation (3 weeks)
| Integrate the car prototype, Ackerman chassis, blind spot detection, lane keeping assist, and adaptive cruise control into a single system |  | 0% | 2024-11-27 | 2024-12-18 | 22
| Run full system simulations, ensuring all features work together seamlessly. |  | 0% | 2024-11-27 | 2024-12-18
| Debug and optimize the complete ADAS system for simulation performance. |  | 0% | 2024-11-27 | 2024-12-18
| Document simulation results for final evaluation. |  | 0% | 2024-11-27 | 2024-12-18
| Revise, Report Writing and gantt Chart Update |  | 0% | 2024-11-27 | 2024-12-18
Final Report and Presentation Preparation (1 week)
| Integrate the car prototype, Ackerman chassis, blind spot detection, lane keeping assist, and adaptive cruise control into a single system |  | 0% | 2024-12-18 | 2024-12-23 | 6
| Run full system simulations, ensuring all features work together seamlessly. |  | 0% | 2024-12-18 | 2024-12-23
| Debug and optimize the complete ADAS system for simulation performance. |  | 0% | 2024-12-18 | 2024-12-23
| Document simulation results for final evaluation. |  | 0% | 2024-12-18 | 2024-12-23
| Revise, Report Writing and gantt Chart Update |  | 0% | 2024-12-18 | 2024-12-23

## About
SIMPLE GANTT CHART by Vertex42.com
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. TimeSheet About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.